## Fact
Information on the progress of the expected implementation of the approved investment program of Kazakhstan-China Pipeline LLP for the IV quarter of 2024.
thousand tenge (excluding VAT)
No. | Name of works | Unit of measurement | Quantity | Plan | Fact* | Execution, % | Deviation
1 | Construction of crossings of Kenkiyak-Kumkol MP facilities | crossing | 2 | 21601.8 | 21601.8 | 100% | 0
2 | Reconstruction of the 10 kV power line of Kenkiyak-Kumkol MP on the section from 90 km to 108 km | km | 18 | 124184.6015 | 124826.091 | 100.5% | 641.4895
3 | Construction of a crossing at 405 km of Kenkiyak-Kumkol MP | crossing | 1 | 57400 | 57400 | 100% | 0
4 | Design and survey work on the development of a working project for the reconstruction of the ECP system | DSW | 1 | 36203.1736 | 36283 | 100.2% | 79.8264
5 | Diagnostics of Kenkiyak - Kumkol MP reservoirs, partial diagnostics of the RVS No. 1 V- 400 m3 at Kenkiyak PA and RVS No. 1, No. 2 V- 400 m3 at the Kumkol PA | service | 3 | 15211.7 | 15211.7 | 100% | 0
6 | Intra-pipe diagnostics of the Kenkiyak-Kumkol oil pipeline | service | 1 | 658955.5 | 658955.52 | 100% | 0.02
7 | Purchase of fixed assets |  |  | 25850.1081 | 45826.0985 | 177.3% | 19975.9904
| TOTAL |  |  | 939406.8831 | 960104.2095 | 102.2% | 20697.3264
Note: *operational data